# Azure Synapse Analytics → Microsoft Fabric

Transformation guide: what changes, why, and the best way to migrate each object

Synapse → Fabric Migration Accelerator · Version 1.1 · 6 October 2026

| Field | Value |
| --- | --- |
| Document | Transformation guide for migrating Azure Synapse workspaces to Microsoft Fabric |
| Audience | Migration leads, data engineers, SQL developers, platform and security administrators, testers |
| Scope | Every object type the accelerator discovers, plus the Synapse services and settings around them |
| Accelerator status | Reflects the accelerator's code on the Rasool branch (Plan & Migrate stages and validation, commit 519c834) |
| Owner | (add name) |
| Reviewers | (add names) |
| Status | Draft for review |

How to read this guide Section 3 is the core: one block per Synapse object type, with the Fabric target, the best way to migrate it, the code that must change and why, how to check it, and the manual work. Every change carries one of four labels: IMPLEMENTED (the accelerator does it today), RULES – NEXT (mechanical, can be automated with rules), AI + REVIEW – NEXT (needs meaning rewritten, automate with an AI step plus human approval) and NEEDS A PERSON (credentials, installs or decisions no tool can make).

Contents

Right-click here and choose Update Field to build the table of contents.

# 1. Executive summary

Fabric is not a new home for the same Synapse code. The SQL engine, Spark runtime and pipeline engine are close relatives, but each has differences that stop Synapse code from running unchanged. A migration therefore has three parts: recreate each object in its Fabric equivalent, transform the code that Fabric would reject, and move and verify the data.

- Most changes are mechanical. Column types, storage clauses, notebook format, pipeline JSON and connection references follow fixed rules. These should be converted by deterministic code, not by hand and not by AI, because rules give the same, testable result every time.

- A smaller set needs meaning rewritten. Serverless SQL over files, credential code in notebooks and mapping data flows cannot be translated line by line. An AI step can draft them, but every draft must be run and compared before a person approves it.

- Some work always needs a person. Secrets cannot be exported from Synapse, gateways must be installed, and choices such as permissions, collation and cut-over timing are business decisions.

- Validation is part of the migration, not an afterthought. Every converted object is compared with its Synapse original before it is trusted.

The status of every change is counted in section 7. Section 8 lists what was missing from the earlier version of this guide.

# 2. Migration approach

## 2.1 Phases

| Assess | → | Prepare Fabric | → | Convert & create | → | Load data | → | Validate | → | Run in parallel | → | Cut over | → | Retire Synapse |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Phase | What happens | Exit criterion |
| --- | --- | --- |
| Assess | Discover every object, classify it, map dependencies into waves, estimate effort, list risks. | Inventory signed off; waves agreed |
| Prepare Fabric | Capacity, workspaces per environment, roles, Git, networking, connections, gateways, collation decision. | Target workspace passes the accelerator's connection test |
| Convert & create | Warehouse, schemas, tables, views, procedures, Spark, notebooks, pipelines, scripts, shortcuts, schedules (switched off). | Every object created or listed with a reason |
| Load data | Historical load per table, sized by row count; then incremental loads until cut-over. | Row counts and totals match |
| Validate | Object-by-object comparison, then functional tests of pipelines and notebooks, then performance tests. | No unexplained differences |
| Run in parallel | Both platforms run the same loads for an agreed period; outputs are compared daily. | Agreed number of clean days |
| Cut over | Freeze Synapse changes, final delta load, switch schedules on, repoint reports and users. | Users on Fabric; no Synapse writes |
| Retire Synapse | Pause the pool, keep it for the rollback window, export logs and history you must keep, then delete. | Rollback window closed |

## 2.2 Principles

- Move in dependency waves. An object moves only after everything it needs exists in Fabric (the accelerator's Dependencies & Waves screen).

- Never overwrite. Re-runs skip what already exists, so a migration can be repeated safely.

- Deterministic first, AI second, people last. Use AI only where rules cannot express the change, and only behind validation.

- One environment at a time. Migrate into development, prove it, then promote through test to production with Git and deployment pipelines.

- Keep Synapse read-only. Discovery and assessment only read; nothing in Synapse is changed until it is retired.

## 2.3 The conversion engine

Every object passes through four layers. Each layer catches what the one above cannot fix safely.

| 1 · Rule converters | Python rules for mechanical changes: types, storage clauses, notebook format, pipeline JSON, connection references. SQL is parsed with a real T-SQL parser (for example sqlglot's tsql dialect or Microsoft's ScriptDom), never with text search alone. |
| --- | --- |
| ▼ |  |
| 2 · Scanner | Rules that flag what layer 1 cannot fix safely: Synapse-only T-SQL, credentials in code, data flows, collation-sensitive comparisons. Today this is the accelerator's pre-run check (preflight). |
| ▼ |  |
| 3 · AI rewrite + review | Only flagged objects, sent with the specific Fabric limitation. The draft is created in a development workspace, run, compared with Synapse, and approved by a person. The diff is kept. |
| ▼ |  |
| 4 · Validation | The accelerator's Validation page compares Synapse and Fabric object by object: columns and types, row counts, definitions, notebook cells, pipeline activities. |

Why not let AI convert everything? An AI model can silently change meaning: rounding, NULL handling, collation, time zones. Its output differs from run to run, so it cannot be re-run safely or audited. Rules are repeatable and testable; AI is kept for the small set of objects whose meaning must be rewritten, and even then nothing reaches production without a run, a comparison and a person's approval. Microsoft's own Migration Assistant for Fabric Data Warehouse (preview) works the same way: an import plus Copilot-suggested fixes that a person reviews.

# 3. Object by object: the best way to migrate each one

Each block below covers one Synapse object type. The labels in the Status column say who does the change today.

## 3.1 Foundation: Fabric capacity and workspaces

| Synapse | Synapse workspace, its region, resource group and DWU / Spark sizing |
| --- | --- |
| Fabric | Fabric capacity (F SKU) and one workspace per environment |
| Accelerator | Fabric Target screen checks the workspace and its capacity |
| Who | Platform administrator |

### Best way to migrate

- Choose a capacity size by measuring, not by converting DWUs: start on a trial or small F SKU, run representative loads, and size from the Capacity Metrics app.

- Create development, test and production workspaces. Put each on the right capacity and region (keep data and compute in the same region as the source storage where possible).

- Assign workspace roles (Admin, Member, Contributor, Viewer) to Entra groups, not individuals.

- Turn on Git integration (Azure DevOps or GitHub) in development, and use deployment pipelines to promote to test and production.

- Run the accelerator's Fabric Target connection test: it confirms sign-in, workspace access and that a capacity is assigned.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| Workspace without a Fabric capacity | Fabric creates no Warehouse, notebook or pipeline in a workspace without capacity. | Assign an F or trial capacity before any migration run. | NEEDS A PERSON |
| Synapse DWU and Spark pool sizing | Fabric bills one shared capacity for all workloads; there is no DWU setting. | Size the capacity from measured load; watch throttling and smoothing in the Capacity Metrics app. | NEEDS A PERSON |

### How to check it worked

- Fabric Target test shows every check passed, including “Fabric capacity assigned”.

### Manual work

- Capacity purchase or trial, workspace creation, role assignment, Git connection.

## 3.2 Dedicated SQL pool → Fabric Warehouse

| Synapse | Dedicated SQL pool |
| --- | --- |
| Fabric | Warehouse (one per pool) |
| Accelerator stage | Warehouse & schema |
| Who | Accelerator, then SQL developer review |

### Best way to migrate

- Decide the collation first. Synapse pools default to case-insensitive; a Fabric Warehouse defaults to case-sensitive. The collation can only be set when the Warehouse is created.

- Create the Warehouse (the accelerator creates it with the pool's name, or reuses it if it exists).

- Map database references: Fabric queries other Warehouses and Lakehouse SQL endpoints in the same workspace by three-part name, so cross-database code can stay in SQL.

- Plan for snapshot isolation: two jobs writing the same table at the same time can conflict, so schedule loads to avoid that.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| Default collation SQL_Latin1_General_CP1_CI_AS (case-insensitive) | A Warehouse defaults to Latin1_General_100_BIN2_UTF8 (case-sensitive): WHERE name = 'abc' and object names behave differently. | Create the Warehouse with the case-insensitive collation, or test every string comparison. | RULES – NEXT |
| SET TRANSACTION ISOLATION LEVEL ... | Fabric Warehouse uses snapshot isolation only. | Remove the statement; retry or serialise conflicting writes. | RULES – NEXT |
| Workload groups, classifiers, resource classes (sp_addrolemember 'largerc') | Fabric manages compute itself; these concepts do not exist. | Delete them; use separate workspaces or capacities to isolate heavy workloads. | RULES – NEXT |
| System views sys.pdw_*, sys.dm_pdw_*, DBCC PDW_SHOWSPACEUSED | They describe Synapse's distributed engine and do not exist in Fabric. | Rethink the purpose (monitoring, sizing) and use Fabric's query insights views or the Monitoring hub. | NEEDS A PERSON |

### How to check it worked

- Validation page: Warehouse exists, schemas match.

Watch out Collation is the change teams most often miss. Agree it with the business before the first run: changing it later means rebuilding the Warehouse.

## 3.3 Schemas

| Synapse | Schemas in the pool |
| --- | --- |
| Fabric | Schemas in the Warehouse |
| Accelerator stage | Warehouse & schema |
| Who | Accelerator |

### Best way to migrate

- Create each schema before its tables (the accelerator orders this automatically). dbo already exists in every Warehouse.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| CREATE SCHEMA | Works the same in Fabric. | Recreated as-is; existing schemas are skipped. | IMPLEMENTED |

### How to check it worked

- Validation page: every schema present.

## 3.4 Tables (definitions)

| Synapse | Tables in the dedicated pool |
| --- | --- |
| Fabric | Tables in the Warehouse |
| Accelerator stage | Warehouse & schema |
| Who | Accelerator, review type notes |

### Best way to migrate

- Rebuild each table from its discovered columns rather than replaying the original DDL: this drops Synapse-only storage clauses by design.

- Map every column type to a supported Fabric type, and record each change so owners can review precision and length.

- Recreate keys as NOT ENFORCED (they guide the optimiser but are not checked), and keep duplicate checks in the load logic.

- Decide how new key values are generated where the source used IDENTITY.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| WITH (DISTRIBUTION = HASH ¦ REPLICATE ¦ ROUND_ROBIN), CLUSTERED COLUMNSTORE INDEX, HEAP, PARTITION (...) on CREATE TABLE | Fabric manages storage layout itself and rejects these options. | Rebuild the table without them. | IMPLEMENTED |
| Types nvarchar, nchar, money, smallmoney, tinyint, datetime, smalldatetime, datetimeoffset, text, ntext, image, xml, time(7), datetime2(7) | Not supported by Fabric Warehouse, or precision capped at 6. | Map to UTF-8 varchar, decimal, smallint, datetime2(≤6), time(≤6), varbinary; every change is noted per column. | IMPLEMENTED |
| PRIMARY KEY, UNIQUE (enforced) | Fabric accepts keys only as NONCLUSTERED ... NOT ENFORCED. | Recreate keys with NOT ENFORCED (not recreated at all today). | RULES – NEXT |
| IDENTITY columns | Fabric's IDENTITY support is newer and more limited than Synapse's (check current limits). | Create the column without IDENTITY and copy existing values unchanged; generate new keys in the load. | IMPLEMENTED |

### How to check it worked

- Validation page compares column names, order and types for every table.

### Manual work

- Owners review the type-change notes for values that could lose precision (for example datetimeoffset loses its offset).

## 3.5 Table data

| Synapse | Rows in pool tables |
| --- | --- |
| Fabric | Rows in Warehouse tables |
| Accelerator stage | Table data |
| Who | Accelerator for small and medium tables; data engineer for large ones |

### Best way to migrate

- Pick the method by size. Up to about 1 million rows per table (the default limit, adjustable): let the accelerator copy rows directly and verify the count.

- Large tables: export from the pool to Parquet in Azure Data Lake with CREATE EXTERNAL TABLE AS SELECT, then load with COPY INTO in Fabric (or a pipeline Copy activity). This is the fastest path and keeps the pool's load low.

- Very large or partitioned tables: export and load partition by partition in parallel, so a failure only repeats one slice.

- Before cut-over: run incremental loads (by date or watermark column) to bring Fabric up to date, then a final delta during the freeze.

- Choose what happens when a Fabric table already has rows: skip it (safe re-runs, the default) or replace it.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| Row copy for tables up to the limit | Fabric needs the rows physically loaded; it cannot read the pool. | Accelerator copies rows with typed casts and checks the count. | IMPLEMENTED |
| Tables above the row limit | A direct row-by-row copy is too slow for them. | Automate CETAS to Parquet + COPY INTO, or generate a pipeline Copy per table. | RULES – NEXT |
| Ongoing changes until cut-over | A one-time copy goes stale while Synapse keeps loading. | Automate incremental loads by watermark column, then a final delta. | RULES – NEXT |

### How to check it worked

- Row counts match (Validation page).

- Add per-column totals or hashes for critical tables (sum of amounts, distinct keys, min/max dates).

### Manual work

- Agree the freeze window and the watermark column per table with data owners.

## 3.6 Views

| Synapse | Views in the pool |
| --- | --- |
| Fabric | Views in the Warehouse |
| Accelerator stage | Warehouse & schema |
| Who | Accelerator, SQL developer for flagged views |

### Best way to migrate

- Create views after the tables they read, in dependency order.

- Run the scanner over each definition first, and fix flagged Synapse-only syntax before creating it.

- Compare a sample of each view's results in both platforms.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| View definition text | Most T-SQL works unchanged. | Recreated from its own text; Fabric's error is reported if rejected. | IMPLEMENTED |
| Encrypted views, or VIEW DEFINITION not granted | The text cannot be read, so the view cannot be recreated. | Get the source from the owner or grant VIEW DEFINITION, then rerun. | NEEDS A PERSON |
| Materialized views | Not supported in Fabric Warehouse. | Replace with a table refreshed by a pipeline, or a plain view if performance allows. | NEEDS A PERSON |

### How to check it worked

- Validation page compares the definition; spot-check results with the same filters on both sides.

## 3.7 Stored procedures

| Synapse | Stored procedures |
| --- | --- |
| Fabric | Stored procedures in the Warehouse |
| Accelerator stage | Warehouse & schema |
| Who | Accelerator, SQL developer review |

### Best way to migrate

- Scan every procedure before creating it, and convert mechanical issues with rules.

- Send only procedures that still fail to the AI rewrite step, with the exact Fabric error and limitation.

- Create, run with test parameters in development, and compare results and side effects with Synapse.

- Watch for statements that change tables (ALTER, RENAME, CTAS): these are where Fabric differs most.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| CTAS or CREATE TABLE with WITH (DISTRIBUTION ...) inside the body | Storage options are rejected by Fabric. | Strip the WITH clause from CTAS (flagged today, not fixed). | RULES – NEXT |
| RENAME OBJECT | Synapse-only syntax. | Rewrite as sp_rename (flagged today, not fixed). | RULES – NEXT |
| OPTION (LABEL = ...) and other query hints | Some hints are not supported in Fabric. | Keep supported hints, remove the rest (flagged today). | RULES – NEXT |
| ALTER TABLE ... ALTER COLUMN and other table changes | Fabric supports a narrower set of ALTER TABLE forms (check the T-SQL surface area page). | Rewrite as create-new, copy, rename. | AI + REVIEW – NEXT |
| COPY INTO ... CREDENTIAL = (IDENTITY = 'Managed Identity') | Synapse's managed identity does not exist in Fabric. | Choose SAS, account key or Entra sign-in, and change the statement. | NEEDS A PERSON |
| Other T-SQL outside Fabric's surface area | Some statements and functions differ between the engines. | Rewrite with AI help, verify by running and comparing. | AI + REVIEW – NEXT |

### How to check it worked

- Each procedure runs in development with test parameters; output tables match Synapse's.

### Manual work

- SQL developer approves every AI-rewritten procedure.

## 3.8 User-defined functions

| Synapse | Scalar and table-valued functions |
| --- | --- |
| Fabric | Functions in the Warehouse |
| Accelerator stage | None yet: functions are not discovered |
| Who | SQL developer today |

### Best way to migrate

- Extend discovery to read functions from the pool catalog (today it reads tables, views and procedures only).

- Create functions before the views and procedures that call them.

- Check each against Fabric's current function support, and rewrite unsupported ones as views or inline logic.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| Functions in the pool | Not discovered, so not migrated. | Add functions to discovery and to the Warehouse stage. | RULES – NEXT |

## 3.9 Security: logins, users, roles and permissions

| Synapse | SQL logins and users, database roles, GRANTs, RLS, column-level security, dynamic data masking, Synapse RBAC |
| --- | --- |
| Fabric | Entra users and groups, workspace roles, item sharing, Warehouse GRANTs, RLS, column-level security, dynamic data masking |
| Accelerator stage | None yet: security is not discovered |
| Who | Security administrator |

### Best way to migrate

- Inventory who has access to what in Synapse (RBAC roles, SQL users, roles, GRANTs, RLS predicates, masks).

- Map people to Entra groups, and groups to Fabric workspace roles (broad access) and Warehouse GRANTs (fine-grained access).

- Recreate row-level security, column-level security and data masking in the Warehouse: Fabric supports all three.

- Test with real user accounts before cut-over.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| SQL logins, CREATE USER WITHOUT LOGIN | Fabric accepts only Entra identities. | Map each to an Entra user or group. | NEEDS A PERSON |
| RLS policies, column permissions, masks | Not discovered today, so not recreated. | Discover them and generate the matching Fabric statements. | RULES – NEXT |
| Synapse RBAC roles | Fabric uses workspace roles and item permissions. | Map roles by agreement with the data owners. | NEEDS A PERSON |

### Manual work

- Access model approved by the security owner; access review after cut-over.

## 3.10 Serverless SQL: databases, external tables, OPENROWSET

| Synapse | Serverless SQL databases, views and external tables over lake files, OPENROWSET queries, credentials |
| --- | --- |
| Fabric | Lakehouse with OneLake shortcuts, queried through its SQL analytics endpoint |
| Accelerator stage | External tables (shortcuts); serverless databases are not discovered yet |
| Who | Accelerator for external tables; data engineer for queries |

### Best way to migrate

- Create OneLake shortcuts to the same storage folders, so the files are read in place and not copied.

- Prefer converting heavily used CSV/Parquet folders to Delta tables in the Lakehouse: only Delta tables appear in the SQL analytics endpoint.

- Rewrite OPENROWSET queries and views to read the Lakehouse tables (Fabric's own OPENROWSET is newer and covers less).

- Move credentials to the Fabric connection behind each shortcut.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| CREATE EXTERNAL TABLE / DATA SOURCE / FILE FORMAT | Fabric reads lake files through shortcuts, not external tables. | OneLake shortcut in a Lakehouse, through the matching connection. | IMPLEMENTED |
| OPENROWSET(BULK 'https://...', FORMAT = 'CSV') scripts | The table design changes: files become shortcut-backed tables. | AI drafts the Lakehouse version; run and compare; person approves. | AI + REVIEW – NEXT |
| Views built over OPENROWSET | Their source becomes a Lakehouse table. | Recreate over the Lakehouse tables (AI draft + review). | AI + REVIEW – NEXT |
| CREATE DATABASE SCOPED CREDENTIAL | Secrets cannot be exported. | New credential on the Fabric connection. | NEEDS A PERSON |
| Serverless databases and their objects | Not discovered today. | Add them to discovery. | RULES – NEXT |

## 3.11 Lake databases

| Synapse | Lake databases (Spark databases and database templates) |
| --- | --- |
| Fabric | Lakehouse tables (Delta) |
| Accelerator stage | None yet: lake databases are not discovered |
| Who | Data engineer |

### Best way to migrate

- Point shortcuts at the existing table folders.

- Convert non-Delta tables (CSV, Parquet) to Delta with a Spark notebook so they appear in the SQL analytics endpoint.

- Update notebooks that query lakedb.table to the Lakehouse's tables.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| Lake database tables (spark.sql("select * from lakedb.t")) | Fabric has Lakehouses, not lake databases; non-Delta tables are not visible to SQL. | Shortcut + convert to Delta, then repoint the code. | RULES – NEXT |

## 3.12 SQL scripts

| Synapse | SQL script items |
| --- | --- |
| Fabric | Notebooks with a T-SQL cell bound to the Warehouse (or saved queries / files in Git) |
| Accelerator stage | SQL scripts |
| Who | Accelerator, then review |

### Best way to migrate

- Classify each script: one that creates objects (already covered by the Warehouse stage), an operational script (keep), or a serverless query (rewrite).

- Keep operational scripts as T-SQL notebooks bound to the Warehouse, or in Git.

- Run each kept script once in development before relying on it.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| SQL script item | Fabric has no SQL script item. | Saved as a notebook with one T-SQL cell, bound to the Warehouse. | IMPLEMENTED |
| Scripts written for serverless SQL | They read lake files, not the Warehouse. | Rewrite against the Lakehouse (see 3.10). | AI + REVIEW – NEXT |

### How to check it worked

- Each kept script runs without error in development.

## 3.13 Notebooks

| Synapse | Synapse notebooks (PySpark, Scala, Spark SQL, .NET) |
| --- | --- |
| Fabric | Fabric notebooks |
| Accelerator stage | Notebooks |
| Who | Accelerator, then data engineer |

### Best way to migrate

- Convert the notebook format and attach a default Lakehouse and Environment.

- Replace storage paths with shortcut paths using a mapping table (storage account and container → Lakehouse and folder).

- Replace Synapse-only utilities and credential calls; read secrets from Azure Key Vault.

- Run each notebook end to end in development and compare its outputs.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| Notebook JSON (bigDataPool, sessionProperties, Synapse cell format) | Fabric uses .ipynb with its own kernel and Lakehouse metadata. | Converted automatically. | IMPLEMENTED |
| abfss://container@account.dfs.core.windows.net/... paths | Work only with storage credentials; OneLake is the Fabric way. | Rewrite to Files/... / Tables/... from a path mapping table (flagged today). | RULES – NEXT |
| mssparkutils.* | Fabric's library is notebookutils (the old name still works, as legacy). | Rename calls. | RULES – NEXT |
| spark.read.synapsesql("pool.schema.table") | Fabric's Warehouse connector uses a different import and the Warehouse name. | Rewrite to Fabric's connector (flagged today). | RULES – NEXT |
| TokenLibrary, linked-service credentials in code | Synapse linked services do not exist in Fabric. | Rewrite to notebookutils.credentials.getSecret (Key Vault) or a connection; AI draft + review (flagged today). | AI + REVIEW – NEXT |
| .NET (C#) notebooks | Fabric has no .NET runtime for Spark. | Rewrite in Python or Scala. | NEEDS A PERSON |

### How to check it worked

- Validation page compares cell counts; run every notebook and compare outputs.

## 3.14 Spark job definitions

| Synapse | Spark job definitions |
| --- | --- |
| Fabric | Spark job definitions |
| Accelerator stage | Spark job definitions |
| Who | Accelerator |

### Best way to migrate

- Recreate with the same main file, arguments and references; set the default Lakehouse.

- Apply the same code changes as notebooks to the job's source files.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| Spark job definition item | Different item format in Fabric. | Recreated automatically. | IMPLEMENTED |

## 3.15 Spark pools, settings and libraries

| Synapse | Apache Spark pools, Spark configurations, pool and workspace libraries |
| --- | --- |
| Fabric | Custom Spark pool + Environment |
| Accelerator stage | Spark pool & environment |
| Who | Accelerator, then data engineer |

### Best way to migrate

- Create a custom pool of the same node size; let it autoscale.

- Create and publish an Environment on the matching runtime (Spark 3.5 → Runtime 1.3; older versions upgrade).

- Upload library files (.whl, .jar, requirements.txt) to the Environment: Synapse stores only their names.

- Retest notebooks against the new Spark and Python versions.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| Spark pool size and settings | Fabric splits them into a pool and an Environment. | Pool + Environment created, runtime mapped. | IMPLEMENTED |
| Library files | Synapse keeps only library names, not the files. | Upload the files to the Environment. | NEEDS A PERSON |
| Spark 3.3 → 3.4 / 3.5, newer Python | Library behaviour can change between versions. | Retest and pin versions. | NEEDS A PERSON |

## 3.16 Pipelines

| Synapse | Synapse pipelines |
| --- | --- |
| Fabric | Data Factory data pipelines |
| Accelerator stage | Pipelines & datasets (after connections, notebooks and Warehouse) |
| Who | Accelerator, then data engineer |

### Best way to migrate

- Migrate connections, notebooks and the Warehouse first: pipelines refer to all three.

- Convert each pipeline: inline its datasets, swap linked services for connections, rename activity types, point SQL-pool steps at the Warehouse.

- Rebuild what has no equivalent (mapping data flows) before migrating the pipelines that call them.

- Run every pipeline once in development and compare what it produced.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| Activity types: Synapse notebook, Spark job, SQL pool stored procedure, Execute pipeline, Script, ForEach, Until, If, Switch, Lookup, Get Metadata, Delete, Validation, Web, Wait, variables, Filter, Fail | Some types are renamed in Fabric; containers must convert their inner activities. | Converted automatically. | IMPLEMENTED |
| Copy with SqlDWSink / SqlDWSource and PolyBase | Fabric loads Warehouses with COPY through its own source and sink types. | DataWarehouseSource / DataWarehouseSink with COPY. | IMPLEMENTED |
| Expressions using @dataset() parameters | Datasets no longer exist. | Values substituted into the activity. | IMPLEMENTED |
| Parameterised linked services (@linkedService()) | Fabric connections are not parameterised the same way. | One connection per target, or dynamic connections where supported. | RULES – NEXT |
| Azure Function, Azure Databricks, Custom (Batch), HDInsight, Machine Learning, Webhook activities | Not converted today, so the pipeline is not migrated. | Map to Fabric's own activities of the same kind (check the current list). | RULES – NEXT |
| Mapping data flows | Fabric has no mapping data flow. | Rewrite as Dataflow Gen2 or a Spark notebook (AI draft + review). | AI + REVIEW – NEXT |

### How to check it worked

- Validation page compares activity counts; run each pipeline and compare outputs.

## 3.17 Datasets

| Synapse | Datasets |
| --- | --- |
| Fabric | No separate item: settings live inside each activity |
| Accelerator stage | Pipelines & datasets |
| Who | Accelerator |

### Best way to migrate

- Nothing to create: their file paths, formats, schemas and parameters are written into each activity that used them.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| Dataset items | Fabric has no dataset item. | Inlined into activities as datasetSettings. | IMPLEMENTED |

## 3.18 Linked services → connections

| Synapse | Linked services |
| --- | --- |
| Fabric | Connections (and gateways for private networks) |
| Accelerator stage | Connections |
| Who | Accelerator + person entering credentials |

### Best way to migrate

- List every linked service and the credential each needs.

- Create one Fabric connection per target; the person enters the credential in the accelerator, which holds it in memory only.

- Where Synapse used its managed identity, choose a new method: service principal, SAS, account key or Fabric workspace identity (same tenant only).

- Skip what Fabric provides itself: the workspace's default linked services, and links to the pool that became the Warehouse.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| Azure SQL, SQL Server, Synapse SQL, Data Lake Gen2, Blob linked services | Fabric uses connections, and needs their credentials. | Connection created; credential typed by a person. | IMPLEMENTED |
| Other types (Key Vault, REST, HTTP, Cosmos DB, Oracle, SFTP and others) | Not mapped today. | Extend the type map to Fabric's matching connection types. | RULES – NEXT |
| Managed identity and stored secrets | Secrets cannot be exported; Synapse's identity does not exist in Fabric (or in another tenant). | New credential per connection. | NEEDS A PERSON |

Different tenants If Synapse and Fabric live in different Microsoft Entra tenants, no identity carries across. Use a service principal from the source tenant, a SAS token or an account key, or move the data into OneLake.

## 3.19 Integration runtimes

| Synapse | Azure (AutoResolve), managed VNet and self-hosted integration runtimes |
| --- | --- |
| Fabric | Built-in compute; on-premises or VNet data gateway |
| Accelerator stage | None: always manual |
| Who | Platform administrator |

### Best way to migrate

- Azure / AutoResolve runtime: nothing to create; Fabric runs cloud work on its own compute.

- Self-hosted runtime: install an on-premises data gateway near the data and bind the connections to it.

- Managed VNet runtime: use a VNet data gateway or managed private endpoints.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| Self-hosted integration runtime | Fabric uses gateways instead. | Install an on-premises data gateway. | NEEDS A PERSON |

## 3.20 Triggers

| Synapse | Schedule, tumbling-window, storage-event and custom-event triggers |
| --- | --- |
| Fabric | Pipeline schedules and event triggers |
| Accelerator stage | Schedules |
| Who | Accelerator, then person at cut-over |

### Best way to migrate

- Convert schedule triggers to pipeline schedules, created switched off.

- Switch schedules on only at cut-over, and switch the Synapse triggers off at the same time.

- Recreate event triggers as Fabric event triggers; redesign tumbling-window logic as a schedule with window parameters.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| Schedule triggers | Fabric schedules belong to each pipeline. | Schedule created, switched off. | IMPLEMENTED |
| Storage-event and custom-event triggers | Different event model in Fabric. | Recreate as Fabric event triggers. | NEEDS A PERSON |
| Tumbling-window triggers | No equivalent in Fabric. | Schedule + window parameters, with backfill logic. | NEEDS A PERSON |

## 3.21 Other Synapse services and settings

| Synapse | Data Explorer pools, Synapse Link, Power BI, networking, Git, monitoring, governance |
| --- | --- |
| Fabric | See the table |
| Accelerator stage | None: not discovered today |
| Who | Platform and data teams |

### Best way to migrate

- Inventory these separately: discovery does not read them today.

- Migrate each with Microsoft's dedicated path for that service, in the order consumers need it.

### Code that must change

| Synapse code or setting | Why Fabric needs a change | Suggested solution | Status |
| --- | --- | --- | --- |
| Data Explorer pools | Fabric's equivalent is a different item. | Eventhouse with KQL databases; re-ingest or attach the data. | NEEDS A PERSON |
| Synapse Link (Cosmos DB, SQL, Dataverse) | Replaced by Fabric's own replication. | Fabric Mirroring. | NEEDS A PERSON |
| Power BI reports on the pool | They point at the old endpoint. | Repoint to the Warehouse, ideally Direct Lake semantic models. | NEEDS A PERSON |
| Managed VNet, managed private endpoints, firewall, exfiltration protection | Fabric has its own network controls. | Private links, managed private endpoints, trusted workspace access. | NEEDS A PERSON |
| Synapse Git repository and release process | Item formats differ; history cannot be converted. | Fabric Git integration and deployment pipelines; keep the old repo read-only. | NEEDS A PERSON |
| Monitoring, alerts and run history | They belong to the Synapse service. | Fabric Monitoring hub, workspace monitoring, Activator alerts; export history you must keep. | NEEDS A PERSON |
| Purview scans, lineage, sensitivity labels | New items need registering. | Fabric lineage, Purview hub, labels on the new items. | NEEDS A PERSON |

# 4. Cross-cutting concerns

| Concern | Why it matters | Suggested solution |
| --- | --- | --- |
| Identity and tenants | Managed identities and secrets never move; different tenants block identity reuse. | Service principals per environment; credentials stored in Key Vault; one owner per connection. |
| Collation | Case-sensitive Fabric default changes query results silently. | Decide before the first run; create the Warehouse with the agreed collation. |
| Capacity and cost | One capacity is shared by SQL, Spark and pipelines; overloads throttle everything. | Separate capacities for production and development; monitor with the Capacity Metrics app. |
| Concurrency | Snapshot isolation can reject concurrent writes to the same table. | Serialise writers per table; add retries to loads. |
| Performance | No distributions or indexes to tune; the engine optimises itself. | Test the slowest queries; keep statistics current; rewrite queries rather than storage. |
| Networking | Private storage and on-premises sources need a route from Fabric. | Gateways, managed private endpoints, trusted workspace access. |
| Environments and CI/CD | Changes must be promoted safely and repeatably. | Git integration in development; deployment pipelines to test and production; environment-specific values outside the code. |
| Testing | Converted code can run but give different answers. | Four levels: object compiles, data matches, pipelines run end to end, users accept. |
| Cut-over and rollback | Users must switch once, with a way back. | Freeze, final delta, switch schedules and reports, keep Synapse paused for the rollback window. |
| Governance | New items lose the old lineage and labels. | Register Fabric items in Purview; reapply sensitivity labels. |
| People | Teams know Synapse, not Fabric. | Runbooks per object type, training before cut-over, named owners per wave. |

# 5. Manual work and owners

| # | Task | Owner | When |
| --- | --- | --- | --- |
| 1 | Buy or assign Fabric capacity; create workspaces; assign roles; connect Git | Platform administrator | Prepare Fabric |
| 2 | Agree the Warehouse collation | Data architect + business owner | Prepare Fabric |
| 3 | Create service principals or SAS tokens; enter credentials for each connection | Platform / security administrator | Prepare Fabric |
| 4 | Install on-premises or VNet data gateways | Platform administrator | Prepare Fabric |
| 5 | Review type-change notes; decide new-key generation for IDENTITY tables | Data owners, SQL developer | Convert |
| 6 | Fix or approve flagged views, procedures and scripts | SQL developer | Convert |
| 7 | Update and test flagged notebook code; upload library files | Data engineer | Convert |
| 8 | Rebuild data flows, event and tumbling-window triggers | Data engineer | Convert |
| 9 | Load large tables; agree watermark columns and freeze window | Data engineer + data owners | Load data |
| 10 | Recreate security: roles, GRANTs, RLS, masks; test with real users | Security administrator | Validate |
| 11 | Sign off validation and the parallel-run period | Migration lead + business owner | Validate / run in parallel |
| 12 | Switch schedules on, repoint reports and users, retire Synapse after rollback window | Migration lead | Cut over / retire |

# 6. Accelerator roadmap: automating the rest

Ordered by value for effort. Rules come first because they are cheap, safe and reusable; AI comes after the scanner can say exactly which objects need it.

| Priority | Work | Covers |
| --- | --- | --- |
| 1 · Rules, quick wins | Collation option at Warehouse creation; keys as NOT ENFORCED; strip storage options from CTAS; RENAME OBJECT → sp_rename; remove isolation and workload statements; mssparkutils → notebookutils; path mapping table; synapsesql rewrite | Most RULES – NEXT items |
| 2 · Data at scale | CETAS + COPY INTO for large tables; partition-parallel loads; incremental loads by watermark; per-column totals in validation | Large tables, cut-over |
| 3 · Discovery gaps | Functions; security (users, roles, GRANTs, RLS, masks); serverless databases; lake databases; networking; Data Explorer; Synapse Link | Items not discovered today |
| 4 · Pipelines breadth | More linked service types; Azure Function, Databricks, Batch, HDInsight, ML and Webhook activities; parameterised connections | Pipelines that are skipped today |
| 5 · AI + review | Serverless rewrites, credential code, data flows, procedures that still fail; always run, compare and approve | All AI + REVIEW – NEXT items |
| 6 · Operations | Hand-off to Git and deployment pipelines; cut-over checklist in the app; post-cut-over monitoring | Cut over and run |

# 7. Status of every change

| Status | Count | Share | Meaning |
| --- | --- | --- | --- |
| IMPLEMENTED | 17 | 26% | The accelerator does it today |
| RULES – NEXT | 19 | 29% | Mechanical; can be automated with rules |
| AI + REVIEW – NEXT | 7 | 11% | Meaning must be rewritten; AI draft, then run, compare, approve |
| NEEDS A PERSON | 23 | 35% | Credentials, installs or decisions |
| Total | 66 | 100% |  |

| Implemented 17 | → | Rules – next 19 | → | AI + review – next 7 | → | Needs a person 23 |
| --- | --- | --- | --- | --- | --- | --- |

## 7.1 Full catalogue

| # | Area | Change | Status |
| --- | --- | --- | --- |
| 1 | Foundation | Workspace without a Fabric capacity | NEEDS A PERSON |
| 2 | Foundation | Synapse DWU and Spark pool sizing | NEEDS A PERSON |
| 3 | Warehouse | Default collation SQL_Latin1_General_CP1_CI_AS (case-insensitive) | RULES – NEXT |
| 4 | Warehouse | SET TRANSACTION ISOLATION LEVEL ... | RULES – NEXT |
| 5 | Warehouse | Workload groups, classifiers, resource classes (sp_addrolemember 'largerc') | RULES – NEXT |
| 6 | Warehouse | System views sys.pdw_*, sys.dm_pdw_*, DBCC PDW_SHOWSPACEUSED | NEEDS A PERSON |
| 7 | Schemas | CREATE SCHEMA | IMPLEMENTED |
| 8 | Tables | WITH (DISTRIBUTION = HASH ¦ REPLICATE ¦ ROUND_ROBIN), CLUSTERED COLUMNSTORE INDEX, HEAP, PARTITION (...) on CREATE TABLE | IMPLEMENTED |
| 9 | Tables | Types nvarchar, nchar, money, smallmoney, tinyint, datetime, smalldatetime, datetimeoffset, text, ntext, image, xml, time(7), datetime2(7) | IMPLEMENTED |
| 10 | Tables | PRIMARY KEY, UNIQUE (enforced) | RULES – NEXT |
| 11 | Tables | IDENTITY columns | IMPLEMENTED |
| 12 | Data | Row copy for tables up to the limit | IMPLEMENTED |
| 13 | Data | Tables above the row limit | RULES – NEXT |
| 14 | Data | Ongoing changes until cut-over | RULES – NEXT |
| 15 | Views | View definition text | IMPLEMENTED |
| 16 | Views | Encrypted views, or VIEW DEFINITION not granted | NEEDS A PERSON |
| 17 | Views | Materialized views | NEEDS A PERSON |
| 18 | Procedures | CTAS or CREATE TABLE with WITH (DISTRIBUTION ...) inside the body | RULES – NEXT |
| 19 | Procedures | RENAME OBJECT | RULES – NEXT |
| 20 | Procedures | OPTION (LABEL = ...) and other query hints | RULES – NEXT |
| 21 | Procedures | ALTER TABLE ... ALTER COLUMN and other table changes | AI + REVIEW – NEXT |
| 22 | Procedures | COPY INTO ... CREDENTIAL = (IDENTITY = 'Managed Identity') | NEEDS A PERSON |
| 23 | Procedures | Other T-SQL outside Fabric's surface area | AI + REVIEW – NEXT |
| 24 | Functions | Functions in the pool | RULES – NEXT |
| 25 | Security | SQL logins, CREATE USER WITHOUT LOGIN | NEEDS A PERSON |
| 26 | Security | RLS policies, column permissions, masks | RULES – NEXT |
| 27 | Security | Synapse RBAC roles | NEEDS A PERSON |
| 28 | Serverless | CREATE EXTERNAL TABLE / DATA SOURCE / FILE FORMAT | IMPLEMENTED |
| 29 | Serverless | OPENROWSET(BULK 'https://...', FORMAT = 'CSV') scripts | AI + REVIEW – NEXT |
| 30 | Serverless | Views built over OPENROWSET | AI + REVIEW – NEXT |
| 31 | Serverless | CREATE DATABASE SCOPED CREDENTIAL | NEEDS A PERSON |
| 32 | Serverless | Serverless databases and their objects | RULES – NEXT |
| 33 | Lake databases | Lake database tables (spark.sql("select * from lakedb.t")) | RULES – NEXT |
| 34 | Scripts | SQL script item | IMPLEMENTED |
| 35 | Scripts | Scripts written for serverless SQL | AI + REVIEW – NEXT |
| 36 | Notebooks | Notebook JSON (bigDataPool, sessionProperties, Synapse cell format) | IMPLEMENTED |
| 37 | Notebooks | abfss://container@account.dfs.core.windows.net/... paths | RULES – NEXT |
| 38 | Notebooks | mssparkutils.* | RULES – NEXT |
| 39 | Notebooks | spark.read.synapsesql("pool.schema.table") | RULES – NEXT |
| 40 | Notebooks | TokenLibrary, linked-service credentials in code | AI + REVIEW – NEXT |
| 41 | Notebooks | .NET (C#) notebooks | NEEDS A PERSON |
| 42 | Spark jobs | Spark job definition item | IMPLEMENTED |
| 43 | Spark | Spark pool size and settings | IMPLEMENTED |
| 44 | Spark | Library files | NEEDS A PERSON |
| 45 | Spark | Spark 3.3 → 3.4 / 3.5, newer Python | NEEDS A PERSON |
| 46 | Pipelines | Activity types: Synapse notebook, Spark job, SQL pool stored procedure, Execute pipeline, Script, ForEach, Until, If, Switch, Lookup, Get Metadata, Delete, Validation, Web, Wait, variables, Filter, Fail | IMPLEMENTED |
| 47 | Pipelines | Copy with SqlDWSink / SqlDWSource and PolyBase | IMPLEMENTED |
| 48 | Pipelines | Expressions using @dataset() parameters | IMPLEMENTED |
| 49 | Pipelines | Parameterised linked services (@linkedService()) | RULES – NEXT |
| 50 | Pipelines | Azure Function, Azure Databricks, Custom (Batch), HDInsight, Machine Learning, Webhook activities | RULES – NEXT |
| 51 | Pipelines | Mapping data flows | AI + REVIEW – NEXT |
| 52 | Datasets | Dataset items | IMPLEMENTED |
| 53 | Connections | Azure SQL, SQL Server, Synapse SQL, Data Lake Gen2, Blob linked services | IMPLEMENTED |
| 54 | Connections | Other types (Key Vault, REST, HTTP, Cosmos DB, Oracle, SFTP and others) | RULES – NEXT |
| 55 | Connections | Managed identity and stored secrets | NEEDS A PERSON |
| 56 | Runtimes | Self-hosted integration runtime | NEEDS A PERSON |
| 57 | Triggers | Schedule triggers | IMPLEMENTED |
| 58 | Triggers | Storage-event and custom-event triggers | NEEDS A PERSON |
| 59 | Triggers | Tumbling-window triggers | NEEDS A PERSON |
| 60 | Other | Data Explorer pools | NEEDS A PERSON |
| 61 | Other | Synapse Link (Cosmos DB, SQL, Dataverse) | NEEDS A PERSON |
| 62 | Other | Power BI reports on the pool | NEEDS A PERSON |
| 63 | Other | Managed VNet, managed private endpoints, firewall, exfiltration protection | NEEDS A PERSON |
| 64 | Other | Synapse Git repository and release process | NEEDS A PERSON |
| 65 | Other | Monitoring, alerts and run history | NEEDS A PERSON |
| 66 | Other | Purview scans, lineage, sensitivity labels | NEEDS A PERSON |

# 8. What this version adds to the earlier guide

- Made general: it describes any Synapse workspace, not one example estate.

- Corrected: recursive CTEs, DML triggers and sequences were listed as Synapse code that Fabric rejects. Dedicated SQL pools do not support them either, so they are not a migration change and were removed.

- Added foundation work: capacity sizing, workspaces per environment, Git and deployment pipelines.

- Added data strategy: size-based load methods, partition-parallel loads, incremental loads and the final delta at cut-over.

- Added object types that were missing: user-defined functions, security (users, roles, RLS, masks), lake databases, serverless databases, integration runtimes in full, other activity and connection types, Data Explorer pools, Synapse Link, Power BI, networking, monitoring and governance.

- Added: ALTER TABLE ... ALTER COLUMN, OPTION (LABEL) and other hints, parameterised linked services, encrypted views, and the tenant problem for identities.

- Added cross-cutting concerns: concurrency, performance, testing levels, cut-over and rollback, people.

- Added owners for every manual task, and a prioritised accelerator roadmap.

- The status count now covers every change in this guide, so it is larger than the 37 changes in the earlier version.

# 9. Risk register

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Collation changes query results unnoticed | High | Medium | Decide collation first; compare results of string filters in validation |
| Converted code runs but gives different answers | High | Medium | Run-and-compare for every converted object; per-column totals |
| Credentials not available when needed | High | High | Collect credentials and owners during Prepare Fabric |
| Capacity too small, throttling during loads | Medium | Medium | Load in off-peak windows; separate production capacity; monitor |
| Large tables take longer than the window | High | Medium | CETAS + COPY INTO, partition-parallel loads, rehearse timings |
| AI rewrite changes meaning | High | Medium | AI only on flagged objects; run, compare and approve every rewrite |
| Missed dependencies break pipelines after cut-over | Medium | Medium | Migrate in waves; run every pipeline end to end before cut-over |
| Users lose access on cut-over day | High | Low | Recreate and test security before cut-over with real accounts |

# 10. Glossary

| Term | Meaning |
| --- | --- |
| Dedicated SQL pool | Synapse's provisioned data warehouse engine. |
| Serverless SQL pool | Synapse's pay-per-query SQL over files in the data lake. |
| Warehouse | Fabric's SQL data warehouse: the target for a dedicated pool. |
| Lakehouse | Fabric item holding files and Delta tables, with a read-only SQL analytics endpoint. |
| OneLake shortcut | A pointer from a Lakehouse to data elsewhere, read in place without copying. |
| Delta | The open table format Fabric uses for Lakehouse tables. |
| Environment | Fabric item holding a Spark runtime version, libraries and Spark settings. |
| Connection | Fabric's stored way of reaching a source, with its credential. Replaces linked services. |
| Data gateway | Software installed near private data so Fabric can reach it. Replaces self-hosted runtimes. |
| CTAS / CETAS | CREATE TABLE AS SELECT / CREATE EXTERNAL TABLE AS SELECT (export a query to files). |
| COPY INTO | T-SQL statement that loads files into a Warehouse table quickly. |
| NOT ENFORCED | A key Fabric records for the optimiser but does not check. |
| Collation | The rules for comparing and sorting text, including whether case matters. |
| Capacity (F SKU) | The compute a Fabric workspace runs on; shared by all its workloads. |
| Wave | A group of objects migrated together because their dependencies are already in Fabric. |

Before relying on a Fabric feature Fabric changes often. IDENTITY columns, OPENROWSET in the Warehouse, event triggers, some activities and Microsoft's migration assistants are new or in preview. Check Microsoft's current pages (“T-SQL surface area in Fabric Data Warehouse”, “Data types in Fabric Data Warehouse”, and the Synapse-to-Fabric migration guides) before a decision depends on them.